## Coversheet
Cyber Incident Response
Decision-Making Matrix
sponsored by

## Cyber Incidents
THIS PLAN IS INTENDED FOR USE WHEN ( INSERT NAME HERE) COUNTY HAS BEEN THREATENED OR IMPACTED WITH A CYBER INCIDENT
Event Name: Cyber Incident Response
Date: 00/00/0000
(Time) 00:00 | EOC Activation Level -? -Estimated Timeframe- ?- Phase of Operation- Preparation (Pre-Incident) | Responsible Entity (ies) | (Complete) Yes-X | (Initials)
| Form a collaborative Planning & Response Coordination Team: At a minimum, the team should initially consist of representatives from- emergency management, critical facility owners and operators, cyber security, law enforcement, legal, information technology, communications, business disaster recovery officials, private industry, and other key stakeholders. Note: Consider starting with your existing critical infrastructure work group. | EM
| Understand the Situation: 1-Identify Critical Assets and Systems: List critical infrastructure, sensitive data, and essential services. 2-Define Risk Assessment Criteria: Establish the criteria for assessing the impact and likelihood of potential incidents. Note: Establishing a confidentiality agreement, Non-Disclosure Agreement (NDA), private-public partnership, or other legal agreement in consultation with appropriate legal advisors may reduce concerns related to: sharing proprietary information, the risk of data leakage, and the potential for brand and financial damages in the event of an incident. | IT/Cyber Security
| To the extent possible- clarify and document system inter- dependencies and vulnerabilities. Note: Some of this information may already be within your existing COOP. | IT/Cyber Security
Place a physical copy of the Continuity of Operations Plan (COOP), Business Continuity Plan (BCP), or Disaster Recovery (DR) Plan in strategic locations if online copy is not accessible after a cyber-attack.
Consult county legal counsel on the steps to declare a local state of emergency to support a cyber incident for logistical needs.
Recommend local legal counsel to represent local government related to cyber insurance policy providers.
Outline and document the consequences of service loss or disruption, with special attention to the problems caused by cyber incidents.
Formulate Cyber-Incident Specific Response Strategies: Develop strategies tailored to different types of cyber incidents (e.g., data breach, ransomware). Determine if a Local State of Emergency (LSE) can/should be implemented. Identify work arounds including (printed materials, portable electronic forms on flash drives)
| Create Communication Plans: Determine communication protocols for internal stakeholders and external parties (media, partners, regulators). | Communications
Review and Update Detection Tools: Regularly update and tune detection systems to adapt to new cybersecurity challenges. Update the consequence management plan based on new findings.
| Develop a schedule to provide regular coordination updates and briefings: Keep all stakeholders informed about potential threats and changes to the consequence management plan. | EM
| Comprehensive Employee Training: Ensure all employees are trained on cybersecurity best practices and their specific roles in the Comprehensive Emergency Management Plan (CEMP). | IT/EM
| Cyber Insurance: Evaluate the need for cyber insurance to mitigate financial risks associated with data breaches. | IT/Finance
| External Support: Establish contacts with external cybersecurity experts and incident response firms. | Finance
| Legal Expert Consultations: Regularly consult with legal experts to ensure compliance with all data protection laws with a focus on local jurisdictions interest. | Legal
| Regulatory Compliance: Ensure all actions comply with relevant laws and regulations regarding cyber security and data breaches. | Legal
| Documentation for Accountability: Maintain detailed records of the incident response and recovery process for auditing and legal purposes. | EM
(Time) 00:00 | EOC Activation Level-?-Estimated Timeframe-?- Phase of Operation-Detection, Analysis & Immediate Response Coordination | Responsible Entity (ies) | (Complete) Yes-X | (Initials)
| Confirm Incident Details: Verify the nature, extent, and potential impact of the cyber incident. | IT/EM
*EOC to Level 2 (Partial Activation) Notify FDEM through EM Constellation. (verify notification via phone call).
Notify State Warning Point of potential incident.
| Activate Emergency Operations Center (EOC): If necessary, activate the EOC to coordinate response efforts. | EM
| Activate the Comprehensive Emergency Management Plan (CEMP), inclusive of the Cyber Incident Response Annex as required. | EM
Communicate with Stakeholders: Inform relevant departments, agencies, public safety organizations, EOC reps, and critical infrastructure partners. (as permitted and allowed)
Public Information: Coordinate with public information officers to release accurate, timely public statements to manage community concerns and media inquiries. (as permitted and allowed)
Incident Command System (ICS): Implement ICS principles to manage the incident efficiently.
Assemble Initial Incident Response Team: Form a team with clear roles and responsibilities, including Information technology security, legal, public relations, cyber incident response firm reps, and management.
*Initiate Situation Report (as needed) for distribution Executive Policy Group (EPG), Board of County Commissioners (BOCC), COMMs) thereafter until threat to County is over. (as permitted and deemed appropriate)
*Designate a PIO point of contact for media.
*Notify Planning Section to be ready for the briefing in the EOC at DATE/TIME
*Initiate IAP and Create WebEOC Event
*Initiate Operations (OPS) team Briefing/Conference Call in EOC (Message Center, Emergency Dispatch Center (EDC)
*Initiate Regional Conference Calls (2am/2pm)
Notify key State, regional and local partners of potential actions or meetings, as appropriate.
Verify critical equipment readiness and locate replacements for any non-operable equipment.
Prepare EOC for Emergency Operations to include testing radios, telephones, & laptops in the OPS Rooms.
Activate COOP as needed and deemed appropriate. Ensure COOP sites are prepped for potential use.
*EM Director Notification to County (Finance Section and Departments) to begin Cost Tracking
Inventory EOC emergency supply stocks, administrative supplies, and forms.
Test EOC Emergency Systems to include communications, power, water, sewage, and shutters (Also GENERATOR FUEL) (Facilities)
Coordinate with ISC if needed (ESF 14 Communications)
(Time) 00:00 | EOC Activation Level-?-Estimated Timeframe- ?- Phase of Operation-Containment, Eradication and Initial Recovery | Responsible Entity (ies) | (Complete) Yes-X | (Initials)
*EOC to Level 1 (Full Activation) Notify FDEM , and verify notification via phone call or back-up communication methods.
Brief County Administrator and elected/non-elected leadership after development of initial assessment, as required. Discuss LSE and determine if applicable.
Establish and maintain incident specific situational awareness.
Set Up Media Room
Identify potential for cascading impacts or additional hazards connected to the incident.
Notify ESFs and State agencies that EOC activities have been initiated.
Containment Procedures: Develop immediate actions to contain the incident and prevent further damage.
Legal and Regulatory Compliance: Ensure all actions comply with legal and regulatory requirements.
Evaluate Infrastructure Impact: Assess the extent of damage to critical infrastructure and community services (utilities, transportation, communications, healthcare).
Resource Allocation: Determine and prioritize immediate resource needs for response and recovery operations.
Community Impact Assessment: Identify the cyber attack's initial effects on the local community, including economic and social impacts. Note: potential longer term impacts will take much more time to determine.
Business Continuity Measures: Deploy temporary measures to continue critical operations during recovery.
Create a new County incident within the appropriate Incident Management Support Tool (WebEOC).
Increase EOC Ops Group activation staffing as appropriate.
Prepare Situation Reports (Sitreps) as warranted
Determine status of communication equipment interoperability; if effected, ensure back-up systems remain operational
Assess how is EOC doing with testing of all equipment-radios, telephones and laptops in OPS Room
(Time) 00:00 | EOC Activation Level-?- Estimated Timeframe-?- Phase of Operation- Recovery & Restoration | Responsible Entity (ies) | (Complete) Yes-X | (Initials)
Activate contingency contracts.
Brief County Administrator and elected/non-elected leadership on key recommended response/recovery/restoration activities, as required
Data Restoration Plans: Implement strategies for data recovery from backups without compromising security.
System Restoration Procedures: Implement steps to safely restore systems to normal operation.
Recovery Planning: Develop and prioritize the list of key, incident specific short-term and long-term recovery activities.
Critical Services Restoration: Prioritize and facilitate the restoration of critical public services.
Financial Assistance: Coordinate with state and federal agencies to secure funding and resources for recovery efforts.
Business Continuity Support: Assist local businesses in resuming operations, including access to recovery resources and information.
Coordinate resource and support requests from responding agencies
*Notify County Administrator of potential initiation of elected/non-elected leadership Group
Continue to facilitate conference calls with all partners on a regularly scheduled basis, as needed.
*Coordinate with County Administrator to contact elected/non-elected leadership members
*Request Additional IT Support for EOC as needed
*Schedule Executive Policy Group Meeting (to include: Court Reporter, County Attorney, ESF 14 (Communications)
Recommend Close Government, Courthouses, Etc.
(Time) 00:00 | EOC Activation Level-?-Estimated Timeframe-?- Phase of Operation- Post-Incident Activities | Responsible Entity (ies) | (Complete) Yes-X | (Initials)
Modify EOC activation staffing as appropriate.
Continue to facilitate conference calls with all partners on a regularly scheduled basis, as needed.
Brief County Administrator and Unified Command Group (UCG) of advisories, as required.
Conduct a Thorough Investigation: Determine the cause and method of the breach to prevent future occurrences.
Review and Learn: Analyze the response to identify weaknesses and improve future responses.
Update CEMP and Related Policies: Revise the management plan and policies based on lessons learned.
Report to Stakeholders: Inform stakeholders about the incident and actions taken, maintaining transparency.
Regular Updates: Provide regular updates to the public and stakeholders about recovery progress and any ongoing threats.
Community Engagement: Hold town hall meetings or forums to address community concerns and collect feedback.
Transparency: Maintain transparency about the challenges and successes of recovery efforts.
Root Cause Analysis: Work with cybersecurity experts to analyze how and why the incident occurred.
Impact Documentation: Document all aspects of the incident’s impact and response for future reference.
*Prepare EPG Briefing and OPS Room if necessary
*Conduct EPG Briefing
Continue to work with cyber security experts to monitor and assess potential state/regional impact using industry specific standards and business continuity resources.
Ensure ESF 14 (Public Information) continues to focus public information campaign specifically on reinforcements of protective actions.
Damage Assessment
Complete Initial Damage Assessment (IDA) ASAP
Continue IAP to Focus on Recovery Efforts.
Coordinate disaster intelligence gathering from all sources.
Re-establish communications to critical facilities (e.g. - Emergency Operations Centers [EOC], hospitals, fire/police stations, etc.).
Assign Government Emergency Telephone System (GETS) cards as needed.
Prepare and Coordinate Local and State Assessment Teams (SAT) for deployment
Determine status of communications networks; re-establish communications to all affected areas, determine needs and requirements.
Prepare communications plan for short-term use of High Frequency (HF) point-to-point, Satellite Communications and National Guard communications support for worst-case disaster areas. If necessary
Coordinate the deployment of emergency communications support teams and assets as needed. (Region ? communications vehicle/ Comm vehicle…)
Collect, analyze, and distribute damage assessment reports.
Ensure ESF 7 (Resource Support) is reporting and tracking all cost/purchases associated with response.
Status of Utility Infrastructure
Insurance claim information
Note on A94: laoc: Are theses in the right place and are they needed here. It appears that they may need to go before the other statement up above
Note on A95: laoc: Same as previous note

## Types of Incidents
THIS PLAN IS INTENDED FOR USE WHEN ( INSERT NAME HERE) COUNTY HAS BEEN THREATENED OR IMPACTED WITH A CYBER INCIDENT
Event Name: Cyber Incident Response
Date: 00/00/0000 |  | Types of Incidents- (Complete) Yes-X
(Time) 00:00 | EOC Activation Level -? -Estimated Timeframe- ?- Phase of Operation- Preparation (Pre-Incident) | Hardware Destruction or Loss | Network Unavailability, Compromise, Degradation, or Destruction | Software Malfunction, Compromise, or Exploitation | Responsible Entity (ies) | (Initials)
| Form a collaborative Planning & Response Coordination Team: At a minimum, the team should initially consist of representatives from- emergency management, fusion center reps,critical facility owners and operators, cyber security, law enforcement, legal, information technology, communications, business disaster recovery officials, private industry, and other key stakeholders. Note: Consider starting with your existing critical infrastructure work group. |  |  |  | EM
| Understand the Situation: 1-Identify Critical Assets and Systems: List critical infrastructure, sensitive data, and essential services. 2-Define Risk Assessment Criteria: Establish the criteria for assessing the impact and likelihood of potential incidents. Note: Establishing a confidentiality agreement, Non-Disclosure Agreement (NDA), private-public partnership, or other legal agreement in consultation with appropriate legal advisors may reduce concerns related to: sharing proprietary information, the risk of data leakage, and the potential for brand and financial damages in the event of an incident. |  |  |  | IT/Cyber Security
| To the extent possible- clarify and document system inter- dependencies and vulnerabilities. Note: Some of this information may already be within your existing COOP. |  |  |  | IT/Cyber Security
Outline and document the consequences of service loss or disruption, with special attention to the problems caused by cyber incidents.
Formulate Cyber-Incident Specific Response Strategies: Develop strategies tailored to different types of cyber incidents (e.g., data breach, ransomware). Determine if a Local State of Emergency (LSE) can/should be implemented. Identify work arounds including (printed materials, portable electronic forms on flash drives)
| Create Communication Plans: Determine communication protocols for internal stakeholders and external parties (media, partners, regulators). |  |  |  | Communications
Review and Update Detection Tools: Regularly update and tune detection systems to adapt to new cybersecurity challenges. Update the consequence management plan based on new findings.
| Develop a schedule to provide regular coordination updates and briefings: Keep all stakeholders informed about potential threats and changes to the consequence management plan. |  |  |  | EM
| Comprehensive Employee Training: Ensure all employees are trained on cybersecurity best practices and their specific roles in the CEMP. |  |  |  | IT/EM
| Cyber Insurance: Evaluate the need for cyber insurance to mitigate financial risks associated with data breaches. |  |  |  | IT/Finance
| External Support: Establish contacts with external cybersecurity experts and incident response firms. |  |  |  | Finance
| Legal Expert Consultations: Regularly consult with legal experts to ensure compliance with all data protection laws with a focus on local jurisdictions interest. |  |  |  | Legal
| Regulatory Compliance: Ensure all actions comply with relevant laws and regulations regarding cyber security and data breaches. |  |  |  | Legal
| Documentation for Accountability: Maintain detailed records of the incident response and recovery process for auditing and legal purposes. |  |  |  | EM
(Time) 00:00 | EOC Activation Level-?-Estimated Timeframe-?- Phase of Operation-Detection, Analysis & Immediate Response Coordination | Hardware Destruction or Loss | Network Unavailability, Compromise, Degradation, or Destruction | Software Malfunction, Compromise, or Exploitation | Responsible Entity (ies) | (Initials)
| Confirm Incident Details: Verify the nature, extent, and potential impact of the cyber incident. | IT/EM |  |  | IT/EM
*EOC to Level 2 (Partial Activation) Notify FDEM through EM Constellation. (verify notification via phone call).
Notify State Warnng Point of incident.
| Activate Emergency Operations Center (EOC): If necessary, activate the EOC to coordinate response efforts. | EM |  |  | EM
| Activate the Comprehensive Emergency Management Plan (CEMP), inclusive of the Cyber Incident Response Annex as required. | EM |  |  | EM
Communicate with Stakeholders: Inform relevant departments, agencies, public safety organizations, EOC reps, and critical infrastructure partners. (as permitted and allowed)
Public Information: Coordinate with public information officers to release accurate, timely public statements to manage community concerns and media inquiries. (as permitted and allowed)
Incident Command System (ICS): Implement ICS principles to manage the incident efficiently.
Assemble Initial Incident Response Team: Form a team with clear roles and responsibilities, including IT security, legal, PR, cyber incident response firm reps, and management.
*Initiate Situation Report (as needed) for distribution (EPG, BOCC, COMMs) thereafter until threat to County is over. (as permitted and deemed appropriate)
*Designate a PIO point of contact for media.
*Notify Planning Section to be ready for the briefing in the EOC at DATE/TIME
*Initiate IAP and Create WebEOC Event
*Initiate Ops team Briefing/Conference Call in EOC (Message Center, EDC)
*Initiate Regional Conference Calls (2am/2pm)
Notify key State, regional and local partners of potential actions or meetings, as appropriate.
Verify critical equipment readiness and locate replacements for any non-operable equipment.
Contact Cleaning Service to ensure backup of supplies.
Prepare EOC for Emergency Operations to include testing radios, telephones, & laptops in the OPS Rooms.
Activate COOP as needed and deemed appropriate. Ensure COOP sites are preppred for potential use.
*EM Director Notification to County (Finance Section and Departments) to begin Cost Tracking
Inventory EOC emergency supply stocks, administrative supplies, and forms.
Test EOC Emergency Systems to include communications, power, water, sewage, and shutters (Also GENERATOR FUEL) (Facilities)
Coordinate with ISC if needed (ESF 14 Communications)
(Time) 00:00 | EOC Activation Level-?-Estimated Timeframe- ?- Phase of Operation-Containment, Eradication and Initial Recovery | Hardware Destruction or Loss | Network Unavailability, Compromise, Degradation, or Destruction | Software Malfunction, Compromise, or Exploitation | Responsible Entity (ies) | (Initials)
*EOC to Level 1 (Full Activation) Notify FDEM , and verify notification via phone call or back-up communication methods.
Brief County Administrator and elected/non-elected leadership after development of initial assessment, as required
Set Up Media Room
Notify ESFs and State agencies that EOC activities have been initiated.
Containment Procedures: Develop immediate actions to contain the incident and prevent further damage.
Legal and Regulatory Compliance: Ensure all actions comply with legal and regulatory requirements.
Evaluate Infrastructure Impact: Assess the extent of damage to critical infrastructure and community services (utilities, transportation, communications, healthcare).
Resource Allocation: Determine immediate resource needs for response and recovery operations.
Community Impact Assessment: Identify the cyber attack's initial effects on the local community, including economic and social impacts. Note: longer term impacts will take much more time to determine.
Business Continuity Measures: Deploy temporary measures to continue critical operations during recovery.
Create a new County incident within the appropriate Incident Management Support Tool (WebEOC).
Increase EOC Ops Group activation staffing as appropriate.
Prepare Sitreps as warranted
Determine status of communication equipment interoperability; if effected, ensure back-up systems remain operational
Assess how is EOC doing with testing of all equipment-radios, telephones and laptops in OPS Room
(Time) 00:00 | EOC Activation Level-?- Estimated Timeframe-?- Phase of Operation- Recovery & Restoration | Hardware Destruction or Loss | Network Unavailability, Compromise, Degradation, or Destruction | Software Malfunction, Compromise, or Exploitation | Responsible Entity (ies) | (Initials)
Activate contingency contracts.
Brief County Administrator and elected/non-elected leadership on key recommended response/recovery/restoration activities, as required
Data Restoration Plans: Implement strategies for data recovery from backups without compromising security.
System Restoration Procedures: Implement steps to safely restore systems to normal operation.
Recovery Planning: Develop and prioritize the list of key, incident specific short-term and long-term recovery activities.
Critical Services Restoration: Prioritize and facilitate the restoration of critical public services.
Financial Assistance: Coordinate with state and federal agencies to secure funding and resources for recovery efforts.
Business Continuity Support: Assist local businesses in resuming operations, including access to recovery resources and information.
*Notify County Administrator of potential initiation of elected/non-elected leadership Group
Continue to facilitate conference calls with all partners on a regularly scheduled basis, as needed.
*Coordinate with County Administrator to contact elected/non-elected leadership members
*Request Additional IT Support for EOC as needed
*Schedule Executive Policy Group Meeting (to include: Court Reporter, County Attorney, HTV, ESF 14 (Communications)
Recommend Close Government, Courthouses, Etc.
(Time) 00:00 | EOC Activation Level-?-Estimated Timeframe-?- Phase of Operation- Post-Incident Activities | Hardware Destruction or Loss | Network Unavailability, Compromise, Degradation, or Destruction | Software Malfunction, Compromise, or Exploitation | Responsible Entity (ies) | (Initials)
Modify EOC activation staffing as appropriate.
Continue to facilitate conference calls with all partners on a regularly scheduled basis, as needed.
Brief County Administrator and UCG of advisories, as required.
Conduct a Thorough Investigation: Determine the cause and method of the breach to prevent future occurrences.
Review and Learn: Analyze the response to identify weaknesses and improve future responses.
Update CEMP and Related Policies: Revise the management plan and policies based on lessons learned.
Report to Stakeholders: Inform stakeholders about the incident and actions taken, maintaining transparency.
Regular Updates: Provide regular updates to the public and stakeholders about recovery progress and any ongoing threats.
Community Engagement: Hold town hall meetings or forums to address community concerns and collect feedback.
Transparency: Maintain transparency about the challenges and successes of recovery efforts.
Root Cause Analysis: Work with cybersecurity experts to analyze how and why the incident occurred.
Impact Documentation: Document all aspects of the incident’s impact and response for future reference.
*Prepare EPG Briefing and OPS Room if necessary
*Conduct EPG Briefing
Continue to work with cyber security experts to monitor and assess potential state/regional impact using industry specific standards and business continuity resources.
Ensure ESF 14 (Public Information) continues to focus public information campaign specifically on reinforcements of protective actions.
Damage Assessment
Complete IDA ASAP
Continue IAP to Focus on Recovery Efforts.
Coordinate disaster intelligence gathering from all sources.
Re-establish communications to critical facilities (e.g. - Emergency Operations Centers [EOC], hospitals, fire/police stations, etc.).
Assign Government Emergency Telephone System (GETS) cards as needed.
Prepare and Coordinate Local and State Assessment Teams (SAT) for deployment
Determine status of communications networks; re-establish communications to all affected areas, determine needs and requirements.
Prepare communications plan for short-term use of High Frequency (HF) point-to-point, Satellite Communications and National Guard communications support for worst-case disaster areas. If necessary
Coordinate the deployment of emergency communications support teams and assets as needed. (Region ? communications vehicle/ Comm vehicle…)
Collect, analyze, and distribute damage assessment reports.
Ensure ESF 7 (Resource Support) is reporting and tracking all cost/purchases associated with response.
Status of Utility Infrastructure
Insurance claim information
Note on A89: laoc: Are theses in the right place and are they needed here. It appears that they may need to go before the other statement up above
Note on A90: laoc: Same as previous note

## ESF Specific Considerations
THIS PLAN IS INTENDED FOR USE WHEN ( INSERT NAME HERE) COUNTY HAS BEEN THREATENED OR IMPACTED WITH A CYBER INCIDENT
Event Name: Cyber Incident Response
Date: 00/00/0000
EOC Activation Level 1/Post Storm +6-24 hours
Coordinate the following Operations Activities:
Deploy Assessment Teams as requested and if required.
Track reentry areas where applicable.
Collect, analyze, and distribute damage assessment reports.
Continue all reporting and information sharing processes.
Coordinate the following Planning Activities:
Conduct long range planning efforts.
Begin planning for long-term shelter based on estimates from field intelligence.
Coordinate the following Logistical Activities:
Coordinate the following Finance Activities:
Ensure ESF 19 (Damage Assessment) is reporting and tracking all damage related cost.
Ensure ESF 7 (Resource Support) is reporting and tracking all cost/purchases associated with response.
Ensure ESF 8 (Public Health) provides status of public health and support systems.
Coordinate with ESF-14 (Communications) to:
Issue news releases on state of the County and provide any additional guidance.
Respond to media inquiries and monitor media.
Distribute press releases.
Additionally, coordinate with ESF-14 (Communications) to work with County agencies and organizations on release of the following types of information:
Status of Utility Infrastructure
Tourism industry oriented information, state park openings
Insurance claim information
EOC Activation Level 1/Post Storm +24-36 hours
Coordinates with FDEM to establish information services as required.
Coordinate with ESF 16 (Law Enforcement with reentry procedures and coordinate with ESF-14 for notification to control points for access passes and/or letters as well as ESF 18 (Business and Industry)
Coordinate with ESF-3 (Public Works) to position signage (variable message boards, road markers) to facilitate reentry, as required.
Ensure ESF-16 (Law Enforcement):
ESF-2 (Communications)
Monitor Status of communications network.
Re-establish communications to critical facilities (e.g., EOCs, hospitals, and shelters).
ESF-3 (Public Works)
Provide information regarding water and sewer system disruption and re-establishment.
Provide information regarding damage to public infrastructure and repair of public infrastructure.
ESF-4 (Fire Fighting)
Monitor and track status of local fires and firefighting capabilities.
Conduct aerial damage assessments of timber and reentry routes.
Coordinate with ESF 3 (Public Works) equipment to assist with debris removal from local and secondary roads.
ESF-10 (Hazardous Materials)
Provide information regarding any known Hazardous Material threats.
ESF-12 (Energy)
Track status of power grid to impacted areas.
Track status of natural gas pipelines and natural gas supplies.
ESF-13(Military Support)
Prepare to execute FLNG recovery operations plan.
ESF-14 (Public Information)
Respond to media inquiries and monitor media.
Distribute press releases.
ESF 3-Public Works - Status of roads
ESF 18-Tourism industry oriented information, State park openings
Inform Public on how to make donations and where to volunteer
Insurance claim information
Status of schools
ESF-16 (Law Enforcement)
Respond to security requirements.
Determine the status of law enforcement and other disaster conditions from local authorities.
Plan, coordinate, and execute law enforcement duties with local and county governments.
ESF 3 (Public Works), ESF 16 (Law Enforcement), Florida Department of Transportation (FDOT)-Emergency Traffic Management
Manage traffic at critical intersections post-impact with priority given to emergency service vehicles, transportation of supplies/equipment, and access to critical facilities.
Assist public and private organizations with traffic control during restoration of infrastructure services.
ESF- 18 (Business and Industry)
Provide liaison with the public sectors business communities to ensure an efficient exchange of plans and information to support recovery operations.
Work with the private sector to assist in focusing efforts and reestablishing commercial operations.
ESF-19 (Damage Assessment)
Provide Liason as necessary to coordinate Damage aassessment activities Countywide
Capture all costs associated with damage assessment in a timely and expedient manner

## Cybersecurity vs.Cyber Incident
1.2. Cybersecurity and Cyber Incident Response- It is important to understand the difference and relationship between cybersecurity and cyber incident response. “Cybersecurity is the art of protecting networks, devices, and data from unauthorized access or criminal use and the practice of ensuring confidentiality, integrity, and availability of information.”2 The goal of cybersecurity is to stop or minimize disruptions. A cybersecurity program is designed to both understand and address cyber risks across an enterprise and is composed of people, processes, and technologies that monitor, detect and, ideally, prevent incidents on an ongoing basis. However, even with the best cybersecurity program in place, cyber incidents are always a risk. Therefore, it is important to have a cyber incident response plan or annex that enables organizations to act quickly. An effective and efficient response helps to mitigate impacts and return functional services as soon as possible. Much of cyber incident response planning occurs before an incident occurs and in conjunction with a cybersecurity program. | Key Questions- Existing Cyber Security Program in place? Is there an existing Business Disaster Recovery Program in place for restoration of IT infrastructure? Do you already have a critical facilities working group that meets regularly to review critical infrastructure vulnerabilities and mitigation needs?
Types of Cyber Incidents-1- Hardware Destruction or Loss: A jurisdiction’s critical services often depend upon the hardware (e.g., computers, industrial control systems, storage devices, network infrastructure) that perform critical functions. This hardware may enable day-to-day community functions, such as controlling drinking water systems and water filtration, managing court processes, providipayment systems for municipal services, and controlling traffic safety systems. It also may support critical emergency services, such as 911 services and radio transmitters used to communicate among emergency personnel. | Types of Cyber Incidents-2-Network Unavailability, Compromise, Degradation, or Destruction: Networks enable computers to communicate and share information. Most critical services rely on networks. Incidents affecting networks may occur because of both natural disasters and malicious attacks. Since many systems depend upon external organizations and are often provided by third parties, an incident affecting the jurisdiction may be the result of a third party’s incident. | Types of Cyber Incidents-3- Software Malfunction, Compromise, or Exploitation: Incidents affecting software may cause the loss or compromise of critical functions. Most of these incidents are caused by human error or accidental misconfigurations. However, incidents affecting software may also result from malicious attacks.

## Sheet1
Compatibility Report for Decision Making Matrix ALL Hazards 04-01-2024 acb edits (1).xls
Run on 5/10/2024 16:03
If the workbook is saved in an earlier file format or opened in an earlier version of Microsoft Excel, the listed features will not be available.
Minor loss of fidelity | # of occurrences | Version
Some cells or styles in this workbook contain formatting that is not supported by the selected file format. These formats will be converted to the closest format available. | 28 | Excel 97-2003